## Task
Project Tasks Management Spreadsheet | [5 empty] | Yellow cells = cells for data entry
| Tasks List | Owner | Project Start | Project Finished | Duration (days) | FTEs | Hrs. | Labor Rate
Project Name
| Tasks List |  | 2008-05-05 | 2008-08-29
| Project manager | Sam | 2008-05-05 | 2008-08-01 | 88 | 0.4 | 281.6 | 35
| Development planning | Jay | 2008-05-05 | 2008-05-28 | 23 | 0.3 | 55.2 | 35
| Budget planning | Mark | 2008-05-24 | 2008-06-03 | 10 | 0.2 | 16 | 35
| Kickoff mtg. | Nancy | 2008-05-17 | 2008-05-17 | 0 | 0.2 | 0 | 20
| Equipments request forms | Bob | 2008-05-24 | 2008-05-28 | 4 | 1 | 32 | 30
| Engneer interviews | Sam | 2008-05-24 | 2008-06-25 | 32 | 0.3 | 76.8 | 30
| System design | Robert | 2008-06-01 | 2008-07-02 | 31 | 1 | 248 | 30
| part1 implemetation | Ron | 2008-07-03 | 2008-07-13 | 10 | 1 | 80 | 30
| part2 implemetation | Alex | 2008-07-08 | 2008-07-13 | 5 | 1 | 40 | 30
| part3 implementation | Jeff | 2008-07-08 | 2008-07-15 | 7 | 1 | 56 | 30
| System integration | Robert | 2008-06-16 | 2008-07-20 | 34 | 1 | 272 | 30
| System debuging | Ron | 2008-07-21 | 2008-07-30 | 9 | 1 | 72 | 30
| System debuging | Alex | 2008-07-21 | 2008-08-03 | 13 | 1 | 104 | 30
| System deployement | Mike | 2008-07-30 | 2008-08-29 | 30 | 1 | 240 | 30
Formulas:
Project Start = MIN([Project Start, row below]:D18)
Project Finished = MAX([Project Finished, row below]:E18)

## Time Line
Project Tasks Time Line
| Tasks List | Owner | Start from day 1 | Duration | Start: | 2008-05-05 | End: | 2008-08-29
Project Name
Tasks List
| Project manager | Sam | 0 | 88
| Development planning | Jay | 0 | 23
| Budget planning | Mark | 19 | 10
| Kickoff mtg. | Nancy | 12 | 0
| Equipments request forms | Bob | 19 | 4
| Engneer interviews | Sam | 19 | 32
| System design | Robert | 27 | 31
| part1 implemetation | Ron | 59 | 10
| part2 implemetation | Alex | 64 | 5
| part3 implementation | Jeff | 64 | 7
| System integration | Robert | 42 | 34
| System debuging | Ron | 77 | 9
| System debuging | Alex | 77 | 13
| System deployement | Mike | 86 | 30

## Budget
Project Labor Budget
| Tasks List | Labor Cost | Hrs. | Labor Rate | Owner
Project Name |  |  | 1112.8
Tasks List
| Project manager | 9856 | 281.6 | 35 | Sam
| Development planning | 1932 | 55.2 | 35 | Jay
| Budget planning | 560 | 16 | 35 | Mark
| Kickoff mtg. | 0 | 0 | 20 | Nancy
| Equipments request forms | 960 | 32 | 30 | Bob
| Engneer interviews | 2304 | 76.8 | 30 | Sam
| System design | 7440 | 248 | 30 | Robert
| part1 implemetation | 2400 | 80 | 30 | Ron
| part2 implemetation | 1200 | 40 | 30 | Alex
| part3 implementation | 1680 | 56 | 30 | Jeff
| System integration | 8160 | 272 | 30 | Robert
| System debuging | 2160 | 72 | 30 | Ron
| System debuging | 3120 | 104 | 30 | Alex
| System deployement | 7200 | 240 | 30 | Mike
| Total Labor Cost | 48972